## Slide 1: Quarterly Review Mission 19th and 20th September 2019
Progress of Antara (Injectable Contraceptive)
In Rajasthan

## Slide 2
In year 2017-18, we started rollout of Injectable contraceptive services in Rajasthan in planned and phased manner.
Identification of high load facilities for Antara roll-out (Total 214 facilities including MCH, DH, SDH, CHCs & PHCs).
A group of master trainer was trained from each districts of Rajasthan.
886 MOs and 1,872 nursing staff were trained in first phase.
All 214 identified facilities were operationalized by the end of FY 2017-18
GOI appreciated Rajasthan for FY 2017-18 for systematic rollout of Injectable Contraceptive under FP program.
Introduction of Injectable contraceptive Antara in Rajasthan (FY -2017-18)
Total New Clients | Total Doses
19,997 | 34,613
Chart: 
| Functional Facilities
DH/SDH (44) | 0.83
CHC (131) | 0.23
PHC (28) | 0.01
Total DH/SDH=53, CHC=579, PHC 2344

## Slide 3
Scaled up Injectable contraceptive services in all districts up to PHC level
To strengthen the facility based counselling RMNCHA counsellors were oriented.
ASHAs were oriented for client mobilization and follow-up.
Since client satisfaction and follow-up is essential to improve continuation rates in a hormonal based next generation contraceptive. There was felt need to establish a systematic client tracking system.
In July 2018 AntaraRaj software was launched for tracking of clients, reminder SMSs, telephonic follow-up (engaging Careline) and for additional demographic details like age and parity of user.
Emphasis was given to use screening checklist and MEC wheel for client selection, and counseling through job-aids at facility level.
In second year, additional 1,320 MOs and 2,280 nursing staff were trained in Rajasthan
Progress of Injectable contraceptive Antara in Rajasthan in FY 2018-19
Chart: 
| Functional Facilities
DH/SDH (52) | 1
CHC (581) | 0.98
PHC (1591) | 0.68
Total New Clients | Total Doses | 2nd Dose Con. | 3rd Dose Con.
88,017 | 1,40,345 | 45% | 45%
Total DH/SDH=52, CHC=595, PHC 2336

## Slide 4
Progress of Injectable contraceptive Antara in Rajasthan in FY 2019-20 (till Aug 2019)
A phasic manner rollout of Antara up to Sub-center level
Translation of injectable manual in Hindi language for ANMs and GNMs.
Orientation of service providers on method effects through video conference.
Strengthening of monitoring, data analysis and reporting (Monthly Antara progress)
Additional 602 MOs and 916 nursing staff were trained till July 2019.
Inclusion of new contraceptive technical update in GNM/ANM curriculum (Planned)
Chart: 
| Functional Facilities
DH/SDH (47) | 1
CHC (595) | 0.97
PHC (1789) | 0.76
SC (1848) | 0.14
Total New Clients | Total Doses | 2nd Dose Con. | 3rd Dose Con.
38,707 | 85,797 | 50% | 57%
Total DH/SDH=47, CHC=614, PHC 2360, SC 13518

## Slide 5
For follow-up visits
Antara Client
MPA Card
AntaraRaj Update
Registration SMS
through AntaraRaj
Reminder SMS
through AntaraRaj
Due List generation and
sharing with FLWs/LHVs
Incentive to ASHA Rs. 100 in MPV districts for each dose
IPC through ASHAs
Self referral
For the 1st time
Client centric approach
FLW Orientation
In Block and sector Meeting
Satisfied Antara client referral
Community Activities:
Saas Bahu Sammelan,
MPV Campaigns & IEC
Strengthening Community Platforms, VHND’s
Purpose
Mitigation of client/spouse anxiety
Triage of side-effects
Reminder for next dose
Health Facility

## Slide 6: Snapshot of Antara progress in Rajasthan.
Year | GOI Supply | Total Clients | Total Doses | Median Age of Users | Average Parity of Users
2017-18 | 93,008 | 19,997 | 34,613 | - | -
2018-19 | 2,34,660 | 88,017 | 1,40,345 | 26 | 2.34
2019-20 | 70,000 | 38,707 | 85,797 | 26 | 2.31
Total | 3,97,668 | 1,46,721 | 2,60,755 | - | -
Chart: Functionality Status
| 2017-18 | 2018-19 | 2019-20
DH | 0.45 | 1 | 1
CHC | 0.15 | 0.98 | 0.97
PHC | 0 | 0.68 | 0.76
SC | 0.14
Chart: 
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | 2017 | 2018 | 2019
2nd dose Con. | 34.7601 | 57.8849 | 49.1937 | 48.2701 | 46.2895 | 43.1606 | 47.9948 | 54.8326 | 60.2426 | 51.711
3rd Dose Con. | #N/A | 64.2703 | 54.1388 | 56.9813 | 54.6117 | 47.5297 | 55.0719 | 55.9087 | 60.8388 | 62.0417